## F2-Timeline-Benchmarks
Date: | Remarks:
2025-07-01 | Beginning of the 2025/2026 academic year
2025-10-01 | Census Day -- the 'as of' date used for the Fall 2 submission; the first Wednesday in October.
2026-02-13 | All SDEM, SASS, CRSE, SCSE, and PSTS data overlapping Census Day should be uploaded to CALPADS by this date. Resolve Submission errors as well as CDD and Certification errors.
Review Certification reports
2/13/2026- 2/20/2026 | Update all data as necessary to be accurate as of Census Day
Verify any updates are reflected correctly in the Aggregate/Supporting report(s)
Send reports to local data stewards, site leaders, and administrators for approval
2/21/2026 - 2/27/2026 | LEA Approval (No Amendment Window)
This is the expected progression of Fall 2 activities and the latest date(s) the activity should be completed.
If the task(s) can be accomplished earlier and the data reviewed sooner, all the better.

## Fall 2 Checklist
2025-2026 CALPADS Fall 2 Checklist
TASK | Responsibility | Date Completed
Fall 2 Preparation
Identify local team. Meet and establish internal deadlines and responsibilities below. The composition of local data management teams will vary, but often include: the CALPADS Coordinator, the Human Resources staff, Curriculum & Instruction Specialist, ELPAC Coordinator, Special Education Coordinator, CTE Coordinator, LEA/Site Administrators, and Site Staff.
Identify LEA staff to be assigned CALPADS user accounts and roles (i.e., LEA Administrator, school level users, etc.…) as needed for local activities.
Ensure staff are informed of essential CALPADS' resources (i.e. system documentation, listservs, CSIS YouTube, etc.). https://www.cde.ca.gov/ds/sp/cl/ https://csis.fcmat.org/
Attend Fall 2 Training, review self-paced videos and/or watch CSIS YouTube videos. https://csis.fcmat.org/ https://www.youtube.com/CSISCALPADSTrainingChannel
Establish communication with Human Resources staff to collect/review staff data
Establish communication with Curriculum & Instructional staff to collect/review course data
Establish communication with Monitoring Authority to address internal questions/issues and determine potential revisions, if needed
Review teaching and non-classroom based assignments that generated exceptions in CalSASS last year (2024-2025). Ensure that:
- Course code or Non Classroom Based or Support Assignment Code reflects the staff's assignment.
- All Local Assignment Options have been populated in the SIS
- Independent Study (IS) Indicator is set to "Y" for any courses delivered via IS
- Departmentalized Standards Grade Level Range reflects the grade level of the standards taught in the course
- Middle School Core Setting Indicator is set to "Y" for any middle school teacher (in grades 5-8) teaching departmentalized courses as part of a middle school core setting
Tool: You can confirm that the correct State Course code is aligned with the appropriate credentials (and vice versa) by accessing CTC's webiste: https://www.ctc.ca.gov/credentials/calsaas-information/appropriate-credentials-for-calpads-course-codes
Real-Time Report: LEAs can now access Real-Time 4.3 report before Fall 2 submission window starts. This means that LEAs can start validating data collected for report 4.3 before the certification reports start generating, so long as you've submitted and posted your Fall 2 files in CALPADS.
Note: COEs can also access C/A 4.3 report before Fall 2 submission window starts. This means that Monitor Authorities (COEs) can also start validating data collected for report 4.3 before the certification reports start generating, so long as you've submitted and posted your Fall 2 files in CALPADS.
Establish communication with CTE Coordinator staff to collect/review postsecondary survey data
Establish responsibility of data and frequency of the following file submissions:
- SSID Enrollment (SENR), Student Information (SINF), Student English Language Acquisition (SELA), Student Program (SPRG)
- Staff Demographics (SDEM)
- Staff Assignments (SASS)
- Course Section Enrollment (CRSE)
- Student Section Enrollment (SCSE)
- Postsecondary Status for CTE Completers (PSTS)
Ensure SIS is continually updated to latest version
Perform audit on SIS data for incomplete staff data
Perform audit on SIS data for inaccurate course data
Perform audit on SIS data for incomplete student section enrollment data
Perform audit on SIS data for incomplete CTE student postsecondary data
Fall 2 - Staff Demographics (SDEM) - Effective Date Processing file type
Identify staff members that can be reported in CALPADS. Do they have a SEID and employed by LEA on Census Day.
All active reportable staff
Obtain\verify 10-digit SEID number from CTC Contact SEID@ctc.ca.gov. https://www.ctc.ca.gov/
Add new staff including Employment start dates, Highest Degree Code, Employment Status code, Staff Service Years, Race\Ethnicity information. Add Employment End Date for staff no longer employed.
Extract, upload, post SDEM records from SIS to CALPADS
Verify all staff have a demographics record (SDEM) - ensure staff counts are correct by designation and school.
Fall 2 - Staff Assignment (SASS) - Full Replacement file type
Identify staff members that can be reported in CALPADS.
Determine applicable supporting staff information that must be reported.
Collect staff assignments to include Job Classification, Non-Classroom Based Assignments, School of Assignment and FTE Percentage.
Verify all staff have an assignment record (SASS) - ensure staff assignments are correct by designation and school.
Extract, upload, post SASS records from SIS to CALPADS
Fall 2 - Course Section Enrollment (CRSE) - Full Replacement file type
Include all Course Section records occurring on Census Day or for school tracks that are not in session on Census Day, the course submission includes the course sections that begin no later than 30 calendar days after Census Day. This is required for all K-12 students. Do not include lunch, free period, or preschool course sections.
CALPADS requires a SEID to identify the teacher who is teaching the course. Exceptions that allow you to submit “9999999999” as the SEID in the course section record: (ROC/P is providing the course, Course Section Instructional Level Code = 23-College Credit Only or 24-Dual Credit, teacher is not an employee of your LEA, Teacher is new)
Review CALPADS File Specifications document for descriptions or and required fields. Review Valid Code Combinations document for Course codes and descriptions. https://www.cde.ca.gov/ds/sp/cl/systemdocs.asp
The State course codes have been changed to facilitate assignment monitoring. They are grouped by: 1000 series – Self-contained (multi-subject) TK – 6th grade primary level, independent study 6000 series – Other related instruction Home room/ study hall, Teacher assistant 7000 – 8000 series – CTE courses 9000 series – Academic content areas (Core/non-core) Math, Foreign language, Science
Extract, upload, post CRSE records from SIS to CALPADS
Fall 2 - Student Course Section Enrollment (SCSE) - Full Replacement file type
Include all Student Course Section Enrollment records occurring on Census Day or for school tracks that are not in session on Census Day, the student course enrollment submission includes the student enrollments in course sections that begin no later than 30 calendar days after Census Day. Do not student include enrollments in lunch, free period, or preschool course sections.
Extract, upload, post SCSE records from SIS to CALPADS
Fall 2 - Postsecondary Status (PSTS) - Full Replacement file type
Establish a process to capture the postsecondary status of the specified students.
Establish a team of resource persons to help identify students who are eligible as well as create a process to gather the data.
Collect PSTS records of CTE completers who completed high school in the prior academic year
To Identify these students check SIS and\or run CALPADS Cohort 15.2 report for grade 12 CTE Completers.
Review the PSTS code sets.
Extract, upload, post PSTS records from SIS to CALPADS
Fall 2 - Certification Validations and Reports
Review and resolve all certification errors
Review and resolve (if applicable) certification warnings
Reconcile English Learner Education Services with EL department
Reconcile Course Section Enrollment with site principals & SPED department
Reconcile Staff Assignments with HR department & Curriculum staff
Credential Analysts/HR Staff should verify that the primary and secondary disabilities of the students in that class (sections reported on the 4.3 report with Instructional Strategy = 700) align with the teacher's Education Specialist authorization.
Reconcile Postsecondary Status results with CTE staff
Distribute certification reports to team members for review and verification
Communicate with Monitoring Authority should there be any questions regarding Assignment Monitoring
Fall 2 certification reports have been reviewed and verified:
2.4 English Learner Education Services - Student Count Unduplicated
2.5 English Learner Education Services - Unduplicated Count of Teachers Providing EL Services
Supporting Reports: 2.6 English Learner - Count by Primary Language 2.7 English Learner Education Services - Student List
3.6 Course Section Enrollment - Count by Content Area
Supporting Reports: 3.1 Class Size - By Content Area 3.2 Class Enrollment - By Content Area 3.3 Class Enrollment - Student List 3.7 Course Section Enrollment - Count and Details 3.8 Course Section Enrollment - Student List
4.1 Staff Count and FTE by Job Classification
Supporting Reports: 4.2 Staff Count and FTE by Job Classification Disaggregated 4.3 Staff Teaching Assignments - Detail 4.4 Staff Profile - List 4.5 Staff Non Classroom Based or Support Assignment - Detail
17.1- Postsecondary Status Outcome - Count
Supporting Reports: 17.2 Postsecondary Status Outcome - Student List

## Cert Report Quality Check
Fall 2 Certification Report Quality Assurance
Fall 2 Certification Reports | Description and Tips
2.4 - English Learner Education Services - Student Count Unduplicated 2.5 - English Learner Education Services - Unduplicated Count of Teachers Providing EL Services | 2.4 - Description: Reports the unduplicated number of English Learners (ELs), with Enrollment Status of “Primary,” and the number of ELs who are receiving EL Education Services. The count is reported from CRSE field 9.20, Education Service code as of Census Day. 2.5 - Description: Reports the unduplicated count of Teachers providing English Language Education Services to English Learners (ELs) with Enrollment Status Code of Primary, Secondary, or Short Term as of Census Day. Tips and What to Look For: Look for any EL student that is not reported in a course with appropriate Education Service (see last column on report 2.4, Service code Missing). Also note: If a student is receiving multiple EL Services Code at a school, the student is counted in only one service per the 'Multiple English Learner Services Report Hierarchy' matrix, which can be found in our User Manual: https://documentation.calpads.org/Glossary/EnglishLanguageAcquisitionData/EnglishLearnerEducationServices/
2.6 - English Learner - Count by Primary Language 2.7 - English Learner Education Services - Student List
3.6 - Course Section Enrollment - Count by Content Area | 3.6 - Description: Reports the course sections of each Local Course within a State Course Code and the number of students enrolled in each local course as of the Fall 2 Report Period. Also reports details about all courses by State Course Code and identified local courses mapped to the state code
3.1 - Class Size - By Content Area 3.2 - Class Enrollment -By Content Area 3.3 - Class Enrollment - Student List 3.7 - Course Section Enrollment - Count and Details 3.8 - Course section Enrollment - Student List
4.1 - Staff Count and FTE by Job Classification | 4.1 - Description: Reports the number of staff and total FTE by job classification, as of the Fall 2 Report Period Tips for Reviewing Report 4.3: Credential Analysts/HR Staff should verify Total Years of Service, sections that have Middle School Core Setting = Y, and Local Assignment Options (LAO). Curriculum and Instruction Staff should verify State Course Codes, Course Content Area Subcategories, Grade Level Range Code for departmentalized courses, Nonstandard Instructional Levels, Education Service English Learners Code, Instructional Language is populated for sections taught in non-English language, Special Day Classes have Instructional Strategy Code = 700, Home Hospital sections have Instructional Strategy Code = 300, Independent Study sections and Distance Learning (aka Online) sections are identified correctly. Tips for Reviewing Report 4.5: Credential Analysts/HR Staff should verify staff are reported with correct NonClassroom Based or Support Assignment for each Job Class: 10-Administrator, 11-Pupil Services, 12-Teacher, 26-NonCertificated Charter School Teacher and 27-Itinerant/Pull-Out/Push-In Teacher.
4.2 - Staff Count and FTE by Job Classification Disaggregated 4.3 - Staff Teaching Assignments - Detail 4.4 - Staff Profile - List 4.5 - Staff Non Classroom Based or Support Assignment - Detail
17.1 - Postsecondary Status Outcome - Count | 17.1 - Description: Reports the total number of CTE completers and CPA students identified in the Postsecondary (PSTS) survey outcome. Report Type: Snapshot / Certification (Fall 2) This report includes: *Students with an enrollment at the School of Attendance any time that overlaps the Fall 1 Graduate From/Through dates for the selected Academic Year (e.g., if PSTS AY = 2025-2026, then EOY3 Graduate From/Through Date would be 8/16/2024 – 8/15/2025) *Enrollment Status = 10 (Primary) or 20 (Secondary) *Grade Levels = 11 or 12 *School Completion Status = 100 (Graduated), 120 (Certificate of Completion), 250 (Adult Ed HS Diploma), 320 (HS Equivalence Certificate), 330 (CHSPE), or 360 (Non-Grad)
17.2 - Postsecondary Status Outcome - Student List